## Budget Tracker
EVENT BUDGET TRACKER ¦ बजट ट्रैकर
Plan in the first columns, then enter what you commit and pay as quotes are accepted. GST is added per category so the tracker matches what vendors will invoice. Sample figures are filled in.
Event | Sangeet + reception, Jaipur |  |  |  | Contingency (% of planned) |  | 7%
Category | Planned ex-GST (₹) | GST % | GST (₹) | Planned incl. GST (₹) | Committed ex-GST (₹) | Committed incl. GST (₹) | Paid so far (₹) | Balance due (₹) | Over / (under) plan ex-GST (₹)
Venue hire, lawn and hall (SAC 997212) | 150000 | 18% |  |  | 150000 |  | 88500
Catering by outside caterer, 350 plates @ ₹1,300 (5%) | 455000 | 5% |  |  | 455000 |  | 143325
Decor, stage and lighting | 320000 | 18% |  |  | 368000 |  | 130272
Sound, DJ and LED wall | 110000 | 18% |  |  | 110000 |  | 0
Photography and video | 120000 | 18% |  |  | 120000 |  | 0
Performers and band | 105000 | 18% |  |  | 105000 |  | 0
Guest logistics and hospitality | 80000 | 18% |  |  | 80000 |  | 0
Sub-total, categories
Contingency reserve (GST added only when spent)
TOTAL PLANNED BUDGET
Contingency used so far (overspend ex-GST)
Contingency remaining
Share of contingency used
GST as a share of the total budget
Committed incl. GST minus planned incl. GST

## Timeline
PLANNING TIMELINE (T-MINUS)
Event date |  | 2026-12-12
T-minus (days) | Due date | Milestone | Owner | Status | Flag
84 |  | Date and venue locked, deposit paid | Planner | Done
70 |  | Caterer chosen, tasting booked | Client + planner | Done
56 |  | Decor design frozen, mood board signed off | Decor lead | Done
42 |  | Performers and band contracted, travel booked | Planner | Done
35 |  | Invitations sent | Client | In progress
28 |  | First guest-count lock, room blocks confirmed | Client | Not started
14 |  | Final count, seating, second vendor instalments paid | Planner | Not started
7 |  | Run of show frozen, call times sent to every vendor | Planner | Not started
1 |  | Rehearsal and site walk-through | Stage manager | Not started
0 |  | EVENT DAY | All | Not started
-7 |  | Vendor settlement, feedback and closeout | Planner | Not started
Formulas:
Flag = IF(AND([Status]<>"Done",[Due date]<TODAY()),"OVERDUE","")
Flag = IF(OR([Status]="",[Status]="Done",[Due date]=""),"",IF([Due date]<TODAY(),"OVERDUE",""))

## Run of Show
RUN OF SHOW ¦ कार्यक्रम क्रम
Separate call times from start times. Vendors arrive at the call time; their service starts at the start time. Draft 6-8 weeks out, add detail at 3-4 weeks, freeze after the walk-through.
Start | Duration (min) | End | Segment | Owner | Location | Cue / notes
14:00 | 240 |  | Decor and stage build (crew call) | Decor lead | Main lawn | Stage 32x12 ft, LED wall hung by 16:00
16:30 | 60 |  | Sound and LED check | Audio lead | Stage | Test entry track, all mics, LED content loop
17:30 | 30 |  | Caterer set-up complete | Catering captain | Buffet and kitchen | Live counters lit, water and welcome drinks staged
18:00 | 30 |  | Staff briefing and walk-through | Planner | Registration | Every owner reads their own rows aloud
18:30 | 30 |  | Doors open, welcome drinks | Guest lead | Entrance | Photographer at the arch
19:00 | 20 |  | Couple entry | Anchor | Stage | LED cue 1, entry track, followspot
19:20 | 40 |  | Sangeet performances | Anchor | Stage | Four family acts, mic cues on the run sheet
20:00 | 60 |  | Dinner service opens | Catering captain | Buffet | Announce from stage, dance floor stays open
21:00 | 60 |  | Live band | Band lead | Stage | Two sets, 5-minute break
22:00 | 30 |  | Cake and speeches | Anchor | Stage | Three speakers, wireless mic check at 21:50
22:30 | 90 |  | DJ set and dance floor | DJ | Dance floor | Hard stop at 00:00 as per the licence
0:00 | 30 |  | Farewell and departures | Guest lead | Entrance | Valet and cab desk
0:30 | 90 |  | Load-out and strike | Stage manager | Lawn | Deposit check with the venue

## Vendors
VENDOR CONTACT AND CALL-TIME SHEET
Vendor | Service | Contact person | Phone | Payment terms | Call time | Contract signed?
[Decor company] | Decor, stage, lighting | [name] | [phone] | 40% booking, 40% T-14, 20% on completion | 14:00 | Yes
[Caterer] | Dinner for 350, 2 live counters | [name] | [phone] | 30% booking, 50% T-7, 20% after | 15:30 | Yes
[Audio / LED] | Sound, DJ, LED wall | [name] | [phone] | 50% booking, balance on the day | 16:00 | Yes
[Band] | Live band, 2 sets | [name] | [phone] | 50% booking, balance before the set | 19:30 | No
[Photo / video] | 1+1 crew | [name] | [phone] | 30% booking, 70% on delivery | 17:30 | Yes