EVENT RUN SHEET ¦ कार्यक्रम क्रम

| Event | Sangeet + reception | Planner | [Name, phone] |
| --- | --- | --- | --- |
| Date | 12 Dec 2026 | Guests | 350 planned, 320 minimum |
| Venue | [Lawn and hall, Jaipur] | Frozen on | 5 Dec 2026 (T-7) |

| Start | Min | End | Segment | Owner | Cue / notes |
| --- | --- | --- | --- | --- | --- |
| 14:00 | 240 | 18:00 | Decor and stage build (crew call) | Decor lead | Stage 32x12 ft, LED wall hung by 16:00 |
| 16:30 | 60 | 17:30 | Sound and LED check | Audio lead | Test entry track, all mics, LED content loop |
| 17:30 | 30 | 18:00 | Caterer set-up complete | Catering captain | Live counters lit, water and welcome drinks staged |
| 18:00 | 30 | 18:30 | Staff briefing and walk-through | Planner | Every owner reads their own rows aloud |
| 18:30 | 30 | 19:00 | Doors open, welcome drinks | Guest lead | Photographer at the arch |
| 19:00 | 20 | 19:20 | Couple entry | Anchor | LED cue 1, entry track, followspot |
| 19:20 | 40 | 20:00 | Sangeet performances | Anchor | Four family acts, mic cues on the run sheet |
| 20:00 | 60 | 21:00 | Dinner service opens | Catering captain | Announce from stage, dance floor stays open |
| 21:00 | 60 | 22:00 | Live band | Band lead | Two sets, 5-minute break |
| 22:00 | 30 | 22:30 | Cake and speeches | Anchor | Three speakers, wireless mic check at 21:50 |
| 22:30 | 90 | 00:00 | DJ set and dance floor | DJ | Hard stop at 00:00 as per the licence |
| 00:00 | 30 | 00:30 | Farewell and departures | Guest lead | Valet and cab desk |
| 00:30 | 90 | 02:00 | Load-out and strike | Stage manager | Deposit check with the venue |

Planning checklist (T-minus)

| Due | Milestone | Owner | Done |
| --- | --- | --- | --- |
| 19 Sep 2026 | Date and venue locked, deposit paid | Planner | [ ] |
| 03 Oct 2026 | Caterer chosen, tasting booked | Client + planner | [ ] |
| 17 Oct 2026 | Decor design frozen, mood board signed off | Decor lead | [ ] |
| 31 Oct 2026 | Performers and band contracted, travel booked | Planner | [ ] |
| 07 Nov 2026 | Invitations sent | Client | [ ] |
| 14 Nov 2026 | First guest-count lock, room blocks confirmed | Client | [ ] |
| 28 Nov 2026 | Final count, seating, second vendor instalments paid | Planner | [ ] |
| 05 Dec 2026 | Run of show frozen, call times sent to every vendor | Planner | [ ] |
| 11 Dec 2026 | Rehearsal and site walk-through | Stage manager | [ ] |
| 12 Dec 2026 | EVENT DAY | All | [ ] |

Rules for the day

1. Vendors arrive at the call time, not the start time.

2. Every segment has one named owner. If a cue has no owner, it does not happen.

3. Only the planner changes this sheet after the freeze, and every change goes to all owners by message.

4. Hard stop for music: 00:00, as per the licence.