## Rollout plan
Hotel software rollout: 30 days to go-live
Go-live date |  | 2026-11-02 | Pick a low-occupancy Monday or Tuesday, never a weekend. Every due date below moves when you change this cell.
# | Task | Days from go-live | Due date | Owner | Status | What "done" looks like
1 | Sign the order and get written exit and data-export terms | -30 |  |  | Not started | Contract signed; export sample file received
2 | List every room type, rate plan, extra-bed and tax rule | -28 |  |  | Not started | One page a front-desk trainee can read
3 | Collect GSTIN, state code, SAC/HSN and place-of-supply settings | -26 |  |  | Not started | Test invoice matches your CA's format
4 | Export guest, corporate-account and advance-booking data from the old system | -24 |  |  | Not started | Row counts recorded before import
5 | Import rooms, rates and 90 days of future bookings | -21 |  |  | Not started | Ten random bookings match the old system
6 | Configure room tariff GST: 5% up to ₹7,500, 18% above | -20 |  |  | Not started | Test bills at ₹6,800 and ₹9,500 read correctly
7 | Configure restaurant, banquet and extras tax lines | -19 |  |  | Not started | Banquet package prints the right rate for your premises
8 | Set user roles: front desk, housekeeping, accounts, owner | -18 |  |  | Not started | Each role sees only what it should
9 | Connect payment gateway or UPI QR and test a refund | -16 |  |  | Not started | One real ₹10 payment and refund done
10 | Connect channel manager or confirm the manual OTA process | -14 |  |  | Not started | A test block closes on one OTA
11 | Set up Form C filing flow for foreign guests | -12 |  |  | Not started | One dummy filing walked through
12 | Train front desk (2 half-days) and housekeeping (1 half-day) | -10 |  |  | Not started | Each trainee checks in a guest unaided
13 | Start the parallel run: enter every day in both systems | -7 |  |  | Not started | Daily variance recorded on the Parallel run sheet
14 | Run a mock night audit with the accountant | -5 |  |  | Not started | Revenue matches to the rupee, or the gap is explained
15 | Fix every variance found in the parallel run | -3 |  |  | Not started | Variance under ₹100 for three days running
16 | Freeze the old system to read-only after a final export | -2 |  |  | Not started | Backup stored in two places
17 | Print offline fallback: guest register and manual bill book | -1 |  |  | Not started | Copies at the front desk
18 | Go live on the new system | 0 |  |  | Not started | First check-in and check-out done
19 | Vendor support on call for the first morning | 1 |  |  | Not started | Direct number saved on every desk phone
20 | First day-close review with owner and accountant | 3 |  |  | Not started | Signed off by both
21 | First week review: complaints, slow screens, missing reports | 7 |  |  | Not started | List sent to vendor with dates
22 | Reconcile OTA payouts against system bookings | 14 |  |  | Not started | Every payout line matched
23 | Run the first GST working from system data | 21 |  |  | Not started | Numbers agree with the return draft
24 | Month-one review and decision to keep, extend or exit the trial | 30 |  |  | Not started | Written note in the file
Tasks done
Tasks blocked
Progress
Overdue (past due date, not done)

## Parallel run
Parallel run: old records against the new system, day by day
Enter each day's total revenue from your manual book and from the new system's day-close report. Go live only after three consecutive days inside your tolerance.
Tolerance (₹) | 100
Date | Manual book total (₹) | New system total (₹) | Variance (₹) | Reason for variance | Inside tolerance (1/0) | Consecutive good days
2026-10-26
2026-10-27
2026-10-28
2026-10-29
2026-10-30
2026-10-31
2026-11-01
2026-11-02
2026-11-03
2026-11-04
Days entered
Days inside tolerance
Longest good run
Ready to go live?

## Data to prepare
Data to have ready before import
Data set | What to check | Who owns it
Room types and inventory | Room numbers, category, bed type, floor, max occupancy, extra-bed rule | Front-office manager
Rate plans | Rack rate, corporate, weekend and seasonal rates; meal plan inclusions | Owner or revenue lead
Tax set-up | GSTIN, state code, SAC for rooms, restaurant and banquet, premises status (specified or not) | Accountant
Future bookings | Next 90 days: guest name, phone, dates, advance paid, source (direct or OTA) | Reservations
Corporate accounts | Company name, GSTIN, credit days, agreed rates, billing contact | Sales and accounts
Advance receipts | Every unadjusted advance with receipt number and date | Accountant
Menu and restaurant items | Item names, prices, tax category, outlet | F&B manager
Banquet enquiries and holds | Date, session, hall, expected guests, quote, hold expiry | Banquet sales
Users and permissions | Who sees rates, who can discount, who can void a bill | Owner
Old-system export | Full export saved before the freeze, stored in two places | Owner or IT contact