## How to use
How to use this workbook
What this is: an event-day workbook for a party lawn, farmhouse or open-air venue. It tracks permissions, estimates generator diesel and the cost to recover, reconciles a decorator's security deposit line by line, and sizes parking.
1. "Permissions": enter the event date. Each item shows its latest safe date. Permission rules vary by city, so the "who to ask" column is a starting point: confirm with your local body, police station and fire office. Change the statuses as you go.
2. "Generator fuel": estimate the diesel an event will burn from the set's kVA rating and the load, then compare it with what the tank dip says afterwards.
3. "Deposit reconciliation": list each deduction from a decorator's or vendor's deposit, mark whether you hold photo evidence, and see the refund. Only evidenced deductions are taken.
4. "Parking": how many cars and two-wheelers to plan for, the area they need, and any shortfall. The area figures are assumptions; measure your own lawn.
5. "Rain plan": decision points and the cost of each action, so the call is made on numbers and not at 4 pm on the day.
Noise rules (Noise Pollution (Regulation and Control) Rules, 2000, verified September 2026): loudspeakers and public address systems are not to be used between 10 pm and 6 am, except inside closed premises such as banquet halls and community halls. A state government may allow use until midnight on festive or cultural occasions for no more than 15 days in a calendar year. At the boundary of a public place, noise may not exceed the area's ambient limit by more than 10 dB or 75 dB, whichever is lower. Residential ambient limits are 55 dB by day and 45 dB by night. An open lawn is not a closed premises, so plan for a 10 pm stop unless your state has permitted more.
Generator figures come from manufacturer-style fuel charts and are planning estimates. Use your own set's datasheet for real work.
Sample figures are illustrative only.

## Permissions
Permissions and readiness checklist
Requirements vary by city. Confirm each item locally. Yellow cells are yours.
Event date | 2026-12-12
Item | Who to ask (confirm locally) | Needed by (days before event) | Latest safe date | Status | Date received | Owner | Notes
Permission for the event on open ground or lawn | Local body or district administration, as your city requires | 30 |  | Not started
Police permission for the event and for loudspeakers or DJ | Local police station, as your city requires | 21 |  | Not started
Fire safety check for tents, pandals and cooking areas | Fire office or your local body | 14 |  | Not started
Music licences for recorded or live music | PPL for sound recordings, IPRS for musical works | 7 |  | Not started
FSSAI licence or registration of the caterer and any kitchen on site | Caterer; confirm category on FoSCoS | 14 |  | Not started
Liquor permission, if alcohol is served | State excise department | 21 |  | Not started
Generator: capacity, earthing, fuel storage, silencer canopy | Your electrician and generator supplier | 7 |  | Not started
Parking plan, marshals, signage, neighbours informed | Venue manager | 7 |  | Not started
Public liability or event insurance, if your policy requires | Your insurer | 14 |  | Not started
Toilets, drinking water and housekeeping staff planned | Venue manager | 3 |  | Not started
First aid, fire extinguishers and marked exits | Venue manager | 3 |  | Not started
Weather plan agreed: tent hire or covered space held | Venue manager and decorator | 7 |  | Not started
Decorator and vendor rules briefed in writing: load-in time, no pits or nails, deposit | Venue manager | 7 |  | Not started
Noise plan: outdoor speakers stop by 10 pm unless the state permits later use | Venue manager and DJ | 3 |  | Not started
Items listed
Received or not needed
Still open
Report date for the late check | 2026-11-20
Open and already past the latest safe date

## Generator fuel
Generator diesel: estimate, then reconcile
Rule of thumb: about 0.2 litres per kVA per hour at full load; part-load factors from typical fuel charts. Use your datasheet for real work.
Generator rating (kVA) | 125
Number of sets running | 1
Expected load (25, 50, 75 or 100 %) | 75%
Hours running (test, event and teardown) | 9
Diesel price per litre (INR, an assumption: enter today's price) | 90
Load | Share of full-load burn
25% | 0.3
50% | 0.52
75% | 0.76
100% | 1
Full-load burn per set (litres per hour)
Burn at expected load (litres per hour per set)
Estimated diesel for the event (litres)
Estimated diesel cost (INR)
Cost per hour of running (INR)
Reconcile after the event
Tank dip before (litres) | 300
Diesel topped up (litres) | 0
Tank dip after (litres) | 118
Diesel actually used (litres)
Actual diesel cost (INR)
Difference from the estimate (litres)
Difference from the estimate (share)
Read it: a large gap means the load was not what you assumed, the set is burning more than its chart, or fuel went somewhere else. Check the hour meter and the tank dip before you argue with a client about the charge.
Sample dip readings are invented.

## Deposit reconciliation
Decorator or vendor security deposit
Deduct only what you can show. Yellow cells are yours.
Vendor (sample) | Decor Studio A
Deposit held (INR) | 50000
Deduction | Photo or written evidence (Y/N) | Amount claimed (INR) | Deducted (INR) | Not deducted: no evidence (INR)
Turf repair where a mandap pit was dug | Y | 6500
Two broken pole lights | Y | 4200
Extra cleaning of the stage area | N | 3000
Nail holes in the wooden gazebo | Y | 1800
Total deducted (INR)
Refund to vendor (INR)
Claims dropped for lack of evidence (INR)
Deductions above the deposit, to recover separately (INR)
Photograph the lawn before the vendor starts and again after strike, with the date and time visible. A deduction with a before and after picture is rarely argued.

## Parking
Parking sizing
The area per vehicle and the marshal ratio are ASSUMPTIONS. Mark out one bay and one lane on your own lawn and measure them.
Expected guests | 500
Share who arrive by car | 60%
People per car | 3.5
Share who arrive on two-wheelers | 15%
People per two-wheeler | 1.3
Share arriving within the same hour (peak overlap) | 85%
Area per car including lanes (sq m, assumption) | 25
Area per two-wheeler including lanes (sq m, assumption) | 3
Parking area you can actually use (sq m) | 3800
Cars per marshal (assumption) | 50
Cars to plan for
Two-wheelers to plan for
Vehicles present at peak
Area needed at peak (sq m)
Area shortfall (sq m)
Cars that fit in the space you have
Marshals to plan
If there is a shortfall, the usual answers are a second field on a short lease, a shuttle from a nearby lot, a valet team with a fixed drop point, or a lower guest cap. Decide before you sell the date, not on the wedding evening.

## Rain plan
Rain plan: decision points and cost
Set each action's cost yourself. The point is to decide on numbers, early.
Decision point | What you check | Action if the forecast is bad | Cost of the action (INR) | Decided by | Triggered (Y/N)
72 hours before | Forecast from at least two sources | Warn the family and the decorator; ask the tent hirer to hold stock | 0
48 hours before | Rain probability and timing at the event hours | Book extra waterproof canopy over the walkways | 25000
24 hours before | Ground condition and drainage | Lay ground mats on the main lawn, move the buffet under cover | 18000
6 hours before | Radar and the last forecast | Switch the ceremony to the covered hall or a fully covered tent | 40000
At event start | Wind and lightning | Hold outdoor lighting and stage power until lightning risk passes | 0
Cost if every action is triggered (INR)
Cost of the actions actually triggered (INR)