## Checklist
RESTAURANT POS TO BANQUET SYSTEM: MIGRATION CHECKLIST
Work top to bottom. Set the status from the drop-down; the Summary sheet counts them. Nothing here needs a vendor login except the export tasks, and you can do those before you sign anything.
# | Area | Task | What to look at | Owner | Status | Notes
1 | Scope | List what the old POS does today for the hall side | Bookings, quotes, advances, receipts, kitchen slips, reports that someone opens weekly | Manager | Not started
2 | Scope | Mark what stays on the restaurant POS | Table service, aggregator orders, daily walk-in billing. Keep these where they are unless a demo proves otherwise | Owner | Not started
3 | Scope | Write the three worst days of last season | A double booking, a wrong tax rate, a lost advance. Each becomes a demo test | Manager | Not started
4 | Export | Export the last 24 months of bookings | Client, date, slot, hall, guest count, amount, advance, balance | Accounts | Not started
5 | Export | Export the customer list | Name, phone, city, event type, source of enquiry. Remove duplicates by phone number | Sales | Not started
6 | Export | Export menu items and rates | Item, category, veg or Jain flag, per-plate cost, per-plate price, tax rate, kitchen station | Chef | Not started
7 | Export | Export open advances and pending balances | Every event that is booked but not fully paid, with dates promised | Accounts | Not started
8 | Export | Export tax invoices for the current financial year | Invoice number, GSTIN, taxable value, tax, place of supply. Keep the PDF originals too | Accounts | Not started
9 | Export | Take a screenshot set of every report you use | You will want to recreate each one, so capture the columns and filters | Manager | Not started
10 | Mapping | Map each menu item to a tax rate | Food served to guests 5% without ITC at ordinary venues; hall rent, decor, sound and other extras 18% | Accounts | Not started
11 | Mapping | Map halls and slots | Morning and evening slots, set-up and pack-down hours, capacity per hall | Manager | Not started
12 | Mapping | Map staff roles and who can see money | Sales sees quotes, accounts sees payments, chef sees quantities only | Owner | Not started
13 | Mapping | Decide the new invoice number series | Sixteen characters at most; separate series for tax invoices, bills of supply and credit notes | Accounts | Not started
14 | Tax | Ask your CA to confirm the rate per line | Especially where hall and food are billed together and where the venue is a specified premises | Accounts | Not started
15 | Tax | Set up advance receipt vouchers | Tax on advances is due when received; the voucher is adjusted on the final invoice | Accounts | Not started
16 | Tax | Check the accounting export with a dummy month | Import the sample into Tally or your accounting tool; compare tax totals with the old system | Accounts | Not started
17 | Test | Enter five real upcoming events by hand | Include one two-day wedding and one corporate booking with TDS | Sales | Not started
18 | Test | Try to double book a slot from two phones at once | The second attempt should be refused, not accepted | Manager | Not started
19 | Test | Print the kitchen sheet for a 400-guest event | Quantities per station, Jain and allergy notes, delivery time | Chef | Not started
20 | Test | Send one quote and one receipt on WhatsApp to your own number | Check the layout on a phone, not on the desktop preview | Sales | Not started
21 | Test | Collect a small advance by UPI and reconcile it | Amount, reference number, receipt sent, balance updated | Accounts | Not started
22 | Cutover | Pick a low-season week for the switch | Never migrate in the fortnight before a peak wedding date | Owner | Not started
23 | Cutover | Freeze new bookings in the old system on a set date | Anything after the date goes only into the new system | Manager | Not started
24 | Cutover | Run both systems for 14 days | Compare daily totals; write down every difference and its cause | Accounts | Not started
25 | Cutover | Train staff in two short sessions | Sales and front desk first, then kitchen and accounts | Manager | Not started
26 | Cutover | Keep read-only access to the old system for the audit period | Do not cancel the subscription until your CA signs off on the year-end | Owner | Not started

## Summary
PROGRESS
Status | Tasks | Share
Not started
In progress
Done
Blocked
Total
Area | Tasks | Done | Done %
Scope
Export
Mapping
Tax
Test
Cutover

## Menu and tax map
MENU ITEM AND TAX MAP (SAMPLE ROWS: OVERWRITE)
One row per item you export. The tax column follows the usual rules for an ordinary venue; your CA decides the final rate for your case.
Item | Category | Diet flag | Kitchen station | Price per plate or unit (INR) | Tax rate | Tax per unit (INR)
Paneer tikka | Starter | Veg | Tandoor | 120 | 5%
Dal makhani | Main | Veg | Main kitchen | 90 | 5%
Jain sabzi | Main | Jain | Jain counter | 85 | 5%
Jalebi live counter | Dessert | Veg | Halwai | 60 | 5%
Hall rent, evening slot | Space |  |  | 120000 | 18%
Stage and lighting package | Extras |  |  | 80000 | 18%
Total tax on one unit of each row