## Event-day run sheet
EVENT-DAY RUN SHEET FOR THE VENUE MANAGER
Event | Kapoor wedding reception, Grand Hall, 7 pm
Guests expected | 340
When | What must be true | Owner | Status | Time done | Notes
T-24 h | Final guest count confirmed in writing and sent to kitchen | Sales | Pending
T-24 h | Advance and balance schedule checked; balance due before the event agreed | Front desk | Pending
T-12 h | Decorator, DJ and caterer confirm arrival times and vehicle numbers for gate entry | Manager | Pending
T-6 h | Hall cleaned, AC pre-cooling started, opening meter photographed | Housekeeping | Pending
T-4 h | Vendor set-up begins under supervision; extra load flagged to the electrician | Manager | Pending
T-3 h | Generator fuel level checked and recorded | Electrician | Pending
T-2 h | Kitchen stations ready; food safety check done | Kitchen head | Pending
T-1 h | Parking and valet staff in position; guest entrance clear | Security | Pending
T-0 | Client family received; manager walks the hall with the host | Manager | Pending
T+2 h | Food service mid-point check: counters stocked, queue length, complaints | Manager | Pending
T+4 h | Music and licence limits checked against local timing rules | Manager | Pending
Close | Guests out; vendor breakdown; closing meter photographed | Manager | Pending
Close + 1 h | Hall handed over clean; damage walk-through signed with client | Housekeeping | Pending
Next day | Final bill prepared from readings, extra plates and damages | Accountant | Pending
Done
Problems open
Percent complete

## Meters and generator
UTILITY READINGS TURNED INTO A BILL LINE
Photograph each meter before and after, then type the numbers here. Rates are examples; use the tariff in your contract. Bill only what the contract allows you to pass on.
Item | Opening | Closing | Rate (Rs) | Amount (Rs)
AC meter, kWh | 4812 | 4930 | 12.5
Stage and lighting meter, kWh | 22140 | 22196 | 12.5
Generator hours | 310 | 314.5 | 1900 |  | Rate per running hour, including diesel, from your contract
Extra AC hours beyond contract | 0 | 2 | 2500
Total utility charge (before GST)
GST at 18% (billed as its own line)
Utility line on the invoice

## Incident log
INCIDENT AND COMPLAINT LOG
Time | Category | Severity (1-3) | What happened | Action taken | Who | Closed? | Summary
19:40 | Power | 3 | Mains dropped for 4 minutes at the stage | Generator took the load; electrician checked the changeover | Electrician | Yes | Severity 1
20:15 | Food | 2 | Live chaat counter ran out of chutney | Kitchen refilled in 10 minutes | Kitchen head | Yes | Severity 2
21:05 | Guest | 1 | Guest asked for a wheelchair ramp | Portable ramp fitted at the side entrance | Manager | Yes | Severity 3
22:30 | Noise | 2 | DJ speakers above the agreed level | Asked to reduce; measured at the door | Manager | Yes | Open items
23:10 | Damage | 2 | Broken glass panel on a display case | Photographed; noted on the damage sheet for the client | Housekeeping | No

## Closing handover
CLOSING HANDOVER TO THE NEXT SHIFT AND TO ACCOUNTS
Item | Done? (Yes/No) | Note
Closing meter and generator readings entered | No
Damage walk-through signed by client | No
Vendor breakdown complete and gate passes returned | No
Balance payment received or promise recorded with date | No
Extra plates and extra hours counted and signed | No
Security deposit decision recorded | No
Lost property logged | No
Cash handed to the accountant with the count sheet | No
Keys, remotes and generator keys returned | No
Tomorrow first event checked for clean turnaround | No
Items complete
Ready to close